## In Progress
| Train - 29* |  |  |  | Train - 30 |  |  |  | Train - 31 |  |  |  | Train - 32 |  |  |  | Train - 33 |  |  |  | Train - 34 |  |  |  | Train - 35 |  |  |  | *Train 32 OCP 4.19.0 Release Window = Oct 2025
Projected 2.15 Release
Train Start Dates | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 |  | Errata | Release Notes
ACM 2.11.8 | 2025-07-10: 2025-07-09; 2025-08-14: 2025-08-14 |  | https://errata.devel.redhat.com/advisory/details/149382 | https://github.com/stolostron/rhacm-docs/blob/2.11_stage/release_notes/errata.adoc
MCE 2.6.8 | 2025-07-10: 2025-07-09; 2025-08-14: 2025-08-14 |  | https://errata.devel.redhat.com/advisory/details/149351
ACM 2.14.1 | 2025-07-31: 2025-07-30; 2025-08-14: 2025-08-13
MCE 2.9.1 | 2025-07-31: 2025-07-30; 2025-08-14: 2025-08-12
ACM 2.10.9 | 2025-07-31: 2025-07-30; 2025-08-21: 2025-08-27 | End of Maintanence support 9/23.2025
MCE 2.5.10 | 2025-07-31: 2025-07-30; 2025-08-21: 2025-08-26 | End of Maintanence support 9/23.2025
ACM 2.13.4 | 2025-08-14: 2025-08-20
MCE 2.8.3 | 2025-08-14: 2025-08-20; 2025-09-04: 2025-09-16
ACM 2.12.5 (Konflux) | 2025-08-28: 2025-09-03; 2025-09-18: 2025-09-24 | Should be Konflux from this release on
MCE 2.7.6 (Konflux) | 2025-08-28: 2025-09-03; 2025-09-18: 2025-09-23
ACM 2.15.0 | [28 empty] | no z-stream planned for month of Oct to focus on 2.15.0 / 2.10.0 | bar: 2025-07-17 to 2025-07-31; 2025-08-14 to 2025-08-21; 2025-09-04; 2025-09-18
MCE 2.10.0 | bar: 2025-07-17 to 2025-07-31; 2025-08-14 to 2025-08-21; 2025-09-04; 2025-09-18
ACM 2.11.9 (Konflux) | bar: 2025-07-17 to 2025-07-31; 2025-08-14 to 2025-08-21; 2025-09-04 to 2025-09-18
MCE 2.6.9 (Konflux) | bar: 2025-07-17 to 2025-07-31; 2025-08-14 to 2025-08-21; 2025-09-04 to 2025-09-18
ACM 2.14.2 | bar: 2025-07-17 to 2025-07-31; 2025-08-14 to 2025-08-21; 2025-09-04 to 2025-09-18
MCE 2.9.2 | bar: 2025-07-17 to 2025-07-31; 2025-08-14 to 2025-08-21; 2025-09-04 to 2025-09-18
No z-stream release for month of Oct to focus on 2.15 release | bar: 2025-07-17 to 2025-07-31; 2025-08-14 to 2025-08-21; 2025-09-04 to 2025-09-18
| Train - 29 |  |  |  | Train - 30 |  |  |  | Train - 31 |  |  |  | Train - 32 |  |  |  | Train - 33 |  |  |  | Train - 34 |  |  |  | Train - 35
ACM Operators | bar: 2025-07-10; 2025-09-04; 2025-10-02; 2025-11-27
Train Start Dates | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18
Submariner | [28 empty] | Note: (Do not delete) - Submariner does not need to be included in ACM QE pipeline post ACM 2.11 release.
Submariner 0.20.1 | 2025-07-17: 2025-07-14; 2025-08-07: 2025-08-14
Submariner 0.19.4 | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Submariner 0.18.5 | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Global Hub | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Global Hub 1.5.1 | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Global Hub 1.4.2 | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Global Hub 1.2.3 | [29 empty] | https://errata.engineering.redhat.com/advisory/147489 | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Gatekeeper | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Gatekeeper 3.17.3 | 2025-08-14: 2025-08-28
Gatekeeper 3.18.1 | 2025-08-14: 2025-08-28
Gatekeeper 3.19.1 | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Gatekeeper 3.19.2 | 2025-08-14: 2025-08-28
VolSync | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
VolSync 0.13.1 | bar: 2025-07-10 to 2025-07-31; 2025-08-14 to 2025-09-18
Milestones
BC: Bug Fix Cut Off
GA: General Availability
Phases
Development
Final Testing
ACM Z-Stream Release Schedule Reference - Historical
Notes
Only bugs with customer cases attached / mentioned get attached to Errata
Release notes review happens as part of doc ticket
Hotfix vs Emergency Release
Planning meeting notes

## ACM MCE Completed
| Shipped | Checked | Notes | Advisory Link
ACM 2.14.0 | 2025-08-01 |  | Released via Konflux | https://gitlab.cee.redhat.com/releng/advisories/-/tree/main/data/advisories/crt-redhat-acm-tenant/2025?ref_type=heads
MCE 2.8.0 | 2025-08-01 |  | Released via Konflux | https://gitlab.cee.redhat.com/releng/advisories/-/tree/main/data/advisories/crt-redhat-acm-tenant/2025?ref_type=heads
ACM 2.14.1 | Next
MCE 2.8.1 | Next
ACM 2.13.1 | 2025-03-25 |  | Emergency Site Config fix | https://errata.devel.redhat.com/advisory/147348
MCE 2.8.1 | 2025-04-08 |  |  | https://errata.engineering.redhat.com/advisory/147179
ACM 2.13.2 | 2025-04-09 |  |  | https://errata.engineering.redhat.com/advisory/147509
ACM 2.13.2 Hot Fix | 2025-05-01 |  | Hotfix for Application Life Cycle Patch instruction | https://errata.devel.redhat.com/advisory/148684
MCE 2.8.2 | 2025-06-03 |  |  | MCE 2.8.2
ACM 2.13.3 | 2025-06-04 |  |  | ACM 2.13.3
MCE 2.8.3 | Next
ACM 2.13.4 | Next
Full Support Ends | 2026-04-17
EOL | 2026-09-18
ACM 2.12.1 | 2024-12-05
MCE 2.7.1 | Skipped |  | (Did not ship - Replaced by MCE 2.7.2)
MCE 2.7.2 | 2024-12-05 |  | (replaces 2.7.1 - no code changes)
ACM 2.12.2 | 2025-01-28 |  | Bug and CVE Release (Jan 2025 CVE due dates) | OCP 4.18 Compatibility Testing completed with this release (week of Feb 12)
MCE 2.7.3 | 2025-01-27 |  | Bug and CVE Release (Jan 2025 CVE due dates) | OCP 4.18 Compatibility Testing completed with this release (week of Feb 12)
ACM 2.12.3 | 2025-04-17 |  |  | https://errata.engineering.redhat.com/advisory/143822
MCE 2.7.4 | 2025-04-17 |  |  | https://errata.engineering.redhat.com/advisory/143847
ACM 2.12.4 | 2025-07-23 |  | Images built on CPaaS and released via CPaaS | https://errata.devel.redhat.com/advisory/148531
MCE 2.7.5 | 2025-07-22 |  | Images built on CPaaS and released via CPaaS | https://errata.devel.redhat.com/advisory/148530
ACM 2.12.5 | Next
MCE 2.7.6 | Next
Full Support Ends | 2026-01-15
EOL | 2026-06-09
ACM 2.11.1 | 2024-07-30 | Y
MCE 2.6.1 | 2024-07-30 | Y
ACM 2.11.2 | 2024-08-29 | Y
MCE 2.6.2 | 2024-08-28 | Y
ACM 2.11.3 | 2024-10-10
MCE 2.6.3 | 2024-10-10
ACM 2.11.4 | 2024-12-17
MCE 2.6.4 | 2024-12-18
ACM 2.11.5 | 2025-01-28 |  | CVE Only Release (Jan 2025 CVE due dates) | https://errata.engineering.redhat.com/advisory/144386
MCE 2.6.5 | 2025-01-28 |  | CVE Only Release (Jan 2025 CVE due dates) | https://errata.engineering.redhat.com/advisory/144387
ACM 2.11.6 | 2025-02-19
MCE 2.6.6 | 2025-02-18
ACM 2.11.7 | 2025-05-07
MCE 2.6.7 | 2025-05-06
ACM 2.11.8 | Next
MCE 2.6.8 | Next
Full Support Ends | 2025-08-15
EOL | 2026-01-26
MCE 2.5.1 (no corresponding ACM) | 2024-03-18 | Y
ACM 2.10.1 | 2024-04-11 | Y
MCE 2.5.2 | 2024-04-10 | Y
ACM 2.10.2 (no corresponding MCE) | 2024-04-24 | Y
ACM 2.10.3 | 2024-05-17 | Y
MCE 2.5.3 | 2024-05-15 | Y
ACM 2.10.4 | 2024-07-10 | Y
MCE 2.5.4 | 2024-07-03 | Y
MCE 2.5.5 | 2024-07-10 | Y
MCE 2.5.6 | 2024-08-29 | Y
ACM 2.10.5 | 2024-09-03 | Y
ACM 2.10.6 | 2024-09-18 | Y
MCE 2.5.7 | 2024-09-17 | Y
ACM 2.10.7 | 2025-01-23 |  | Bug and CVE Release (Jan 2025 CVE due dates) | https://errata.engineering.redhat.com/advisory/138990
MCE 2.5.8 | 2025-01-23 |  | Bug and CVE Release (Jan 2025 CVE due dates) | https://errata.engineering.redhat.com/advisory/138987
ACM 2.10.8 | 11003058 |  | Bug and CVE Release (Jan 2025 CVE due dates) | https://errata.devel.redhat.com/advisory/details/145341
MCE 2.5.9 | 2025-05-05 |  | Bug and CVE Release (Jan 2025 CVE due dates) | https://errata.devel.redhat.com/advisory/details/145239
ACM 2.10.9 | Next
MCE 2.5.10 | Next
Full Support Ends | 2024-10-22
EOL | 2025-09-23
MCE 2.4.1 | 2023-11-29 | Y | (No Corresponding ACM)
ACM 2.9.1 | 2023-12-13 | Y
MCE 2.4.2 | 2023-12-13 | Y
ACM 2.9.2 | 2024-01-18 | Y
MCE 2.4.3 | 2024-01-18 | Y
ACM 2.9.3 | 2024-03-14 | Y
MCE 2.4.4 | 2024-03-11 | Y
ACM 2.9.4 | 2024-06-04 | Y
MCE 2.4.5 | 2024-06-03 | Y
ACM 2.9.5 | 2024-10-28
MCE 2.4.6 | 2024-10-28
ACM 2.9.6 | 2025-01-21 |  | CVE Only Release (Jan 2025 CVE due dates) | https://errata.engineering.redhat.com/advisory/140413
MCE 2.4.7 | 2025-01-21 |  | CVE Only Release (Jan 2025 CVE due dates) | https://errata.engineering.redhat.com/advisory/140414
ACM 2.9.7 | 2025-02-13 |  |  | https://errata.engineering.redhat.com/advisory/145234
MCE 2.4.8 | 2025-02-12 |  |  | https://errata.engineering.redhat.com/advisory/145238
ACM 2.9.8 | 2025-04-01 |  | Emergency fix for one bug | https://errata.engineering.redhat.com/advisory/146288
ACM 2.9.9 | 2025-06-03 |  |  | ACM 2.9.9
MCE 2.4.9 | 2025-06-02 |  |  | MCE 2.4.9
Full Support Ends | 2024-07-16
EOL | 2025-06-17
ACM 2.8.4 | 2024-11-30 | Y |  | CT for OCP 4.14
MCE 2.3.4 | 2024-11-30 | Y |  | CT for OCP 4.14
ACM 2.8.5 | 2024-02-14 | Y
MCE 2.3.5 | 2024-02-14 | Y
ACM 2.8.6 | 2024-04-03 | Y
MCE 2.3.6 | 2024-04-02 | Y
ACM 2.8.7 | 2024-07-30 | Y
MCE 2.3.7 | 2024-07-29 | Y
ACM 2.8.8 | 2024-11-21
MCE 2.3.8 | 2024-11-21
Full Support Ended | 2024-07-09
EOL | 2024-12-10
ACM 2.7.10 | 2023-12-11 | Y
MCE 2.2.10 | 2023-12-11 | Y
ACM 2.7.11 | 2024-02-07 | Y
MCE 2.2.11 | 2024-02-06 | Y
MCE 2.2.12 | 2024-03-18 | Y
ACM 2.7.12 | 2024-03-18 | Y
ACM 2.7.13 | 2024-06-05 | Y
MCE 2.2.13 | 2024-06-05 | Y
EOL | 2024-08-16
ACM 2.6.8 (CVE Fix) | 2024-10-30 | Y |  | Do not count in totals
MCE 2.1.9 (CVE Fix) | 2024-10-30 | Y |  | Do not count in totals
EOL | 2023-12-13
Sprint #
Dates
Week Start
Milestone Date
MTC 1.5.5/1.6.5
MTC 1.7.2
MTC 1.8
MTC 1.7.3
MTC 1.7.4
MTC 1.7.5
MTRHO
MTC 1.7.7
MTC 1.7.8
Milestone Dates - Related Products
OCP 4.11
OCP 4.12 (TARGET/TENTATIVE)
ODF 4.11
ODF 4.12 (TARGET/TENTATIVE)
OADP 1.0.7
Lifecycle Support Page:
Red Hat Advanced Cluster Management for Kubernetes Lifecycle
ACM Z-Stream Release Schedule Reference - Historical

## Operators Completed
|  |  |  | 249 | 250 | 251
| Shipped | Checked | [5 empty] | Advisory Link | Checked
Global Hub 0.7.1 | 2023-11-20 | [7 empty] | Yes
Global Hub 1.0.1 | 2023-12-12 | [7 empty] | Yes
Global Hub 1.0.2 | 2024-02-26 | [7 empty] | Yes
Global Hub 1.1.1 | 2024-05-28 | [6 empty] | https://errata.devel.redhat.com/advisory/details/129570 | Yes
Global Hub 1.1.2 | 2024-08-29 | [6 empty] | https://errata.devel.redhat.com/advisory/132927 | Yes
Global Hub 1.2.1 | 2025-01-22 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/137006 | Yes
Global Hub 1.2.2 | 2025-04-01 | [6 empty] | https://errata.engineering.redhat.com/advisory/145197 | Yes
Global Hub 1.2.3 | 2025-06-23 | [6 empty] | https://errata.engineering.redhat.com/advisory/147489 | Yes
Global Hub 1.3.1 | 2024-11-26 | [6 empty] | https://errata.engineering.redhat.com/advisory/142390 | Yes
Global Hub 1.3.2 | 2025-01-21 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/143794 | Yes
Global Hub 1.3.3 | 2025-04-14 | [6 empty] | https://errata.devel.redhat.com/advisory/145195 | Yes
Global Hub 1.4.1 | 2025-06-02 | [6 empty] | https://errata.devel.redhat.com/docs/show/147489 | Yes
Global Hub 1.4.2 | 2025-08-05 | [5 empty] | First Konflux z-stream | https://gitlab.cee.redhat.com/rhtap-release/advisories/-/raw/main/data/advisories/acm-multicluster-glo-tenant/2025/15521/advisory.yaml
Global Hub 1.5.0 | 2025-07-21 | [5 empty] | Released via Konflux | https://access.redhat.com/errata/RHEA-2025:11454 | Yes
Gatekeeper 3.14.1 | 2024-05-30 | [7 empty] | Yes
Gatekeeper 3.14.2 | 2024-11-18 | [7 empty] | Yes
Gatekeeper 3.14.3 | 2025-02-12 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/144609 | Yes
Gatekeeper 3.15.1 | 2024-07-18 | [7 empty] | Yes
Gatekeeper 3.15.2 | 2024-11-18 | [7 empty] | Yes
Gatekeeper 3.15.3 | 2025-02-12 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/144613 | Yes
Gatekeeper 3.15.4 | 2025-03-20 | [7 empty] | Yes
Gatekeeper 3.17.1 | 2025-02-12 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/144727 | Yes
Gatekeeper 3.17.2 | 2025-03-20 | [7 empty] | Yes
Gatekeeper 3.19.0 | 2025-07-23 | [6 empty] | https://access.redhat.com/errata/RHEA-2025:11484
Volsync v0.8.1 | 2024-03-07 | [6 empty] | https://errata.devel.redhat.com/advisory/128375 | Yes
Volsync v0.8.2 | 2024-06-04 |  | https://errata.engineering.redhat.com/advisory/129518 |  |  |  |  | https://errata.devel.redhat.com/advisory/129518 | Yes
Volsync v0.9.1 | 2024-04-11 | [6 empty] | https://errata.devel.redhat.com/advisory/129523 | Yes
Volsync v0.9.2 | 2024-06-26 |  | https://errata.devel.redhat.com/advisory/131741 |  |  |  |  | https://errata.devel.redhat.com/advisory/131741 | Yes
Volsync v0.9.3 | 2024-08-26 |  | (Double check) CVE fix |  |  |  |  | https://errata.devel.redhat.com/advisory/137549 | Yes
Volsync v0.10.1 | 2024-09-17 | Y | Labeled as RHEA - should be RHSA? |  |  |  |  | https://errata.devel.redhat.com/advisory/138635 | Yes
VolSync 0.10.2 | 2025-01-16 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/144550 | Yes
Volsync 0.11.1 | 2025-01-16 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/144551 | Yes
Volsync 0.11.2 | 2025-04-16 | [6 empty] | https://errata.devel.redhat.com/advisory/147296 | Yes
VolSync 0.12.1 | 2025-03-25 | [5 empty] | Fix Pack for CVEs - Ideally released earlier than ACM 2.13.1 - get done as soon as volsync team can - testing & shipping eod mar 25 tues - two days prior to acm 2.13.2 cut off | https://errata.engineering.redhat.com/advisory/147296 | Yes
VolSync 0.13.0 | 2025-07-14 | [5 empty] | Released via Konflux | https://access.redhat.com/errata/RHEA-2025:10993 | Yes
Submariner 0.14.7 | 2023-12-04 |  | EOL is nearing - CVEs (depends on date images are ready d/s - will make the call) | [5 empty] | Yes
Submariner 0.14.8 | Skipped | [7 empty] | advisory dropped
Submariner 0.14.9 | 2024-08-05 |  | Note: Found a bug in 0.14.8 testing, will be doing a 0.14.9 release with the bugfix and any CVEs. Did we skip 0.14.8 | [5 empty] | Yes
Submariner 0.15.3 | 2023-11-28 | [7 empty] | Yes
Submariner 0.15.4 | Skipped | [7 empty] | Per Canvas in Slack; advisory dropped
Submariner 0.15.5 | 2024-07-31 |  | Note: Found a bug in 0.15.4 testing, will be doing a 0.15.5 release with the bugfix and any CVEs. Skipped 0.15.4 | [5 empty] | Yes
Submariner 0.16.2 | 2023-11-20 | [7 empty] | Yes
Submariner 0.16.3 | 2024-02-05 | [7 empty] | Yes
Submariner 0.16.4 | Skipped | [7 empty] | advisory dropped
Submariner 0.16.5 | Skipped | [7 empty] | Per slack message skipped to 0.16.7 after 0.16.3
Submariner 0.16.6 | Skipped | [7 empty] | advisory dropped
Submariner 0.16.7 | 2024-07-01 | [7 empty] | Yes
Submariner 0.16.8 | 2025-01-23 | [5 empty] | Jan 25 CVE related | https://errata.devel.redhat.com/advisory/144731
Submariner 0.17.1 | 2024-04-29 |  | https://errata.devel.redhat.com/advisory/130604 | [5 empty] | Yes
Submariner 0.17.2 | 2024-07-11 | [7 empty] | Yes
Submariner 0.17.3 | Skipped | [7 empty] | Yes
Submariner 0.17.4 | 2024-11-26
Submariner 0.17.5 | 2025-01-29 | [5 empty] | Jan 25 CVE related | https://errata.engineering.redhat.com/advisory/140411
Submariner 0.18.1 | Skipped | [7 empty] | Yes
Submariner 0.18.2 | 2024-11-07 | [7 empty] | Yes
Submariner 0.18.3 | 2024-01-07 | [5 empty] | (Not part of Jan 2025 CVE remediation) | https://errata.engineering.redhat.com/advisory/143892 | Yes
Submariner 0.18.4 | 2025-01-16 | [6 empty] | https://errata.engineering.redhat.com/advisory/144541 | Yes
Submariner 0.19.1 | Skipped | [7 empty] | Yes
Submariner 0.19.2 | 2025-02-04 | [5 empty] | Jan 25 CVE related | https://errata.devel.redhat.com/advisory/145262 | Yes
Submariner 0.19.3 | 2025-03-19 | [6 empty] | https://errata.devel.redhat.com/advisory/147177 | Yes
Submariner 0.19.4 | 2025-04-29
Submariner 0.20.1

## Planning Discussion
1. Active Release Stream chart ACM Active Release Streams
During OCP Y stream release window & subsequent ACM Y stream release target - there should only be one z-stream release planned
Highlight for ACM and MCE compatibility testing with OCP Y stream [Note: Release Stream 4 Should Equal z-stream for OCP Y compatibility testing]

## Container Grades
Release Stream | Last Release | LR Date | Errata | Grades | Last Check | EOL | ME
ACM 2.8 z stream | 2.8.7 | 2024-07-30 | https://errata.engineering.redhat.com/advisory/129989 | C(155 A,16 C) | 2024-10-05 | 2024-12-10
MCE 2.3 z stream | 2.3.7 | 2024-07-29 | https://errata.engineering.redhat.com/advisory/129937 | C(136 A,12 C) | 2024-10-05 | 2024-12-10
ACM 2.9 z stream | 2.9.5 | 2024-10-28 | https://errata.engineering.redhat.com/errata/container/132968?cache_mode=update_changed | D(155 A,16 C,4 D) | 2024-10-05
MCE 2.4 z stream | 2.4.6 | 2024-10-28 | https://errata.engineering.redhat.com/errata/container/132942?cache_mode=update_changed | D(132 A,12 C,4 D) | 2024-10-05
ACM 2.10 z stream | 2.10.6 | 2024-09-18 | https://errata.engineering.redhat.com/advisory/138423 | C(172 C,3 A) | 2024-12-20
MCE 2.5 z stream | 2.5.7 | 2024-09-17 | https://errata.engineering.redhat.com/advisory/138472 | C(148 C,4 A) | 2024-12-20
ACM 2.11 z stream | 2.11.2 | 2024-08-29 | https://errata.engineering.redhat.com/advisory/136941 | B(164 B,7 A) | 2024-10-05
MCE 2.6 z stream | 2.6.2 | 2024-08-28 | https://errata.engineering.redhat.com/advisory/136939 | B(27 A,112 B) | 2024-10-05
ACM 2.12 z stream
MCE 2.7 z stream
Operators

## Sheet6
| Train-09 |  |  |  | Train-10 |  |  |  | Train-11 |  |  |  | Train - 12 |  |  |  | Train - 13 |  |  |  | Train - 14 |  |  |  | Train - 15 |  |  |  | Train - 16 |  |  |  | Notes |  |  | 249 | 250 | 251
OCP 4.16 Release Window
Train Start Dates | 2023-11-30 | 2023-12-07 | 2023-12-14 | 2023-12-21 | 2023-12-28 | 2023-01-04 | 2023-01-11 | 2023-01-18 | 2023-01-25 | 2023-02-01 | 2023-02-08 | 2023-02-15 | 2023-02-22 | 2/29 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2024-04-25 | 2024-05-02 | 2024-05-09 | 2024-05-16 | 2024-05-23 | 2024-05-30 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 2024-06-27 | 2024-07-04 |  |  | Docs Issue
ACM 2.8.6 | 2023-03-21: 2024-03-22; 2023-03-28: 2024-04-03
MCE 2.3.6 | 2023-03-21: 2024-03-22; 2023-03-28: 2024-04-02
ACM 2.10.1 | 2023-03-21: 2024-03-25; 2023-04-04: 2024-04-10
MCE 2.5.2 | 2023-03-21: 2024-03-25; 2023-04-04: 2024-04-11
ACM 2.10.2 (Obs Bug Only) | 2023-04-18: 2024-04-24
ACM 2.10.3 | 2023-04-11: 2024-04-22 | Decision: Release only 1 z stream during this train
MCE 2.5.3 (Proposed - Open to Suggestions)
ACM 2.9.4 (Draft) | 2023-04-11: 2024-04-17; 2024-04-25: 2024-05-02 | RHEL Release Freeze moved to 29 & 30-April - adjusted GA by 1 Day
MCE 2.4.5 (Draft) | 2023-04-11: 2024-04-17; 2024-04-25: 2024-05-01 | RHEL Release Freeze moved to 29 & 30-April - adjusted GA by 1 Day
ACM 2.7.13 (Draft) | 2023-04-11: 2024-04-17; 2024-05-02: 2024-05-08 |  | Discussion - FInal Release for this stream
MCE 2.2.13 (Draft) | 2023-04-11: 2024-04-17; 2024-05-02: 2024-05-07 |  | Full Support Ends 3/7/2024; Maintenance Support Ends 7/9/2024
ACM 2.10.2 (Draft) | 2024-05-09: 2024-05-15; 2024-05-23: 2024-05-29
MCE 2.5.3 (Draft) | 2024-05-09: 2024-05-15; 2024-05-23: 2024-05-28
ACM 2.8.7 (Draft) | 2024-05-09: 2024-05-15; 2024-05-30: 2024-06-05
MCE 2.3.7 (Draft) | 2024-05-09: 2024-05-15; 2024-05-30: 2024-06-04
ACM 2.10.3 (Draft) | 2024-06-06: 2024-06-12; OCP 4.16 Release Window 2024-06-20: 2024-06-26 | REQUIRED FOR OCP 4.16 COMPATIBILITY TESTING | Discussion - are these dates too close together?
MCE 2.5.4 (Draft) | 2024-06-06: 2024-06-12; OCP 4.16 Release Window 2024-06-20: 2024-06-25 | REQUIRED FOR OCP 4.16 COMPATIBILITY TESTING | Discussion - are these dates too close together?
ACM 2.9.5 (To be moved to next z stream slot) | 2024-06-06: 2024-06-12; OCP 4.16 Release Window 2024-06-27: 2024-07-03 | Note early July holidays in US and CAN; no release freeze in place | Vote to move out
MCE 2.4.6 (To be moved to next z stream slot) | 2024-06-06: 2024-06-12; OCP 4.16 Release Window 2024-06-27: 2024-07-02 | Note early July holidays in US and CAN; no release freeze in place | Vote to move out
RISK: Westford Outage (Dates tba - Robyn to check for updates)
ACM Operators | [12 empty] | 2023-02-22 | 2/29 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2024-04-25 | 2024-05-02 | 2024-05-09 | 2024-05-16 | 2024-05-23 | 2024-05-30 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 2024-06-27 | 2024-07-04
GlobalHub 1.1.1 | [12 empty] | 2024-05-09: 2024-05-15; 2024-05-23: 2024-05-29 | Align with ACM 2.10.2
Submariner | [9 empty] | 2024-02-05
GateKeeper 3.14.1 (Proposed) | [11 empty] | 2023-02-21 | 2024-05-09: 2024-05-09
Volsync v0.9.1 | [12 empty] | 2023-03-28: 2024-04-10 | Release alongside ACM 2.10.1
Volsync v0.8.2 | [12 empty] | 2024-04-25: 2024-05-01 | Release alongside ACM 2.9.4
OCP 4.16 Release Window | [32 empty] | OCP 4.16 - Release Window = June 2024 | bar: 2024-05-23 to 2024-06-27
Y Stream: MCE 2.6/ACM 2.11 | [12 empty] | 2024-06-27: 2024-06-27 | Projected Y stream Dates: MCE 2.6 (6/27/2024) and ACM 2.11 (7/8/2024)
Milestones
BC: Bug Fix Cut Off
GA: General Availability
Phases
Development
Final Testing
ACM Z-Stream Release Schedule Reference - Historical
BF Cut off - 4th Thursday of every train
In theory, nothing 1st of train (no deadlines, releases, etc)

## Template
[13 empty] | Train - 15 |  |  |  | Train - | Train - | Train - | Train - | Train -
Please note that some release streams are in DRAFT status
Train Start Dates | [12 empty] | 2024-05-16 | 2024-05-23 | 2024-05-30 | 2024-06-06
ACM Release Stream 1
MCE Release Stream 1
ACM Release Stream 2
MCE Release Stream 2
ACM Release Stream 3
MCE Release Stream 3
ACM Release Stream 4
MCE Release Stream 4
ACM Release Stream 1
MCE Release Stream 1
ACM Release Stream 2
MCE Release Stream 2
ACM Release Stream 3
MCE Release Stream 3
ACM Release Stream 4
MCE Release Stream 4
ACM Release Stream 1 | [21 empty] | During OCP Y stream release window & subsequent ACM Y stream release target - there should only be one z-stream release planned
MCE Release Stream 1
[Note: Release Stream 1 Should Equal z-stream for OCP Y compatibility testing] | [21 empty] | Highlight for ACM and MCE compatibility testing with OCP Y stream
[Note: Release Stream 1 Should Equal z-stream for OCP Y compatibility testing]
[9 empty] | Train - 14 |  |  |  | Train - 15 |  |  |  | Train - | Train - | Train - | Train - | Train -
ACM Operators
Train Start Dates | 2023-02-22 | 2/29 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2024-04-25 | 2024-05-02 | 2024-05-09 | 2024-05-16 | 2024-05-23 | 2024-05-30 | 2024-06-06
Submariner | [21 empty] | Note: (Do not delete) - Submariner does not need to be included in ACM QE pipeline post ACM 2.11 release. | bar: 2/29 to 2023-03-07; 2023-03-28 to 2023-04-04; 2024-04-25 to 2024-05-02; 2024-05-23 to 2024-05-30
GateKeeper | bar: 2/29 to 2023-03-07; 2023-03-28 to 2023-04-04
Global Hub | bar: 2/29 to 2023-03-07; 2023-03-28 to 2023-04-04
Volsync | bar: 2/29 to 2023-03-07; 2023-03-28 to 2023-04-04
Milestones
BC: Bug Fix Cut Off
GA: General Availability
Phases
Development
Final Testing
ACM Z-Stream Release Schedule Reference - Historical

## Planning 2
| Train - 25 |  |  |  | Train - 26 |  |  |  | Train - 27 |  |  |  | Train - 28* |  |  |  | Train - 29* |  |  |  | Train - 30 |  |  |  | OCP 4.19.0 Release Window = June 2025* (Target first Tuesday of window June 3)
Please note that some release streams are in DRAFT status | ACM 2.13 Release Window
Train Start Dates | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07
[25 empty] | Notes | Notes (cont) | Advisory Link | Link to publish to the OCP 4.14 Catalog | Docs Jira | HYPBLD Jira | RM Jira | bar: 2025-02-27; 2025-03-27; 2025-04-24; 2025-05-22 to 2025-07-17
ACM Release Stream 1 | 2025-03-20: 2025-03-26; 2025-04-03: 2025-04-09
MCE Release Stream 1 | 2025-03-20: 2025-03-26; 2025-04-03: 2025-04-08
ACM Release Stream 2 | 2025-03-20: 2025-03-26; 2025-04-10: 2025-04-16
MCE Release Stream 2 | 2025-03-20: 2025-03-26; 2025-04-10: 2025-04-15
ACM Release Stream 3 | 2025-04-17: 2025-04-23; 2025-05-01: 2025-05-07
MCE Release Stream 3 | 2025-04-17: 2025-04-23; 2025-05-01: 2025-05-06
ACM Release Stream 4 | 2025-04-17: 2025-04-23; 2025-05-08: 2025-05-14
MCE Release Stream 4 | 2025-04-17: 2025-04-23; 2025-05-08: 2025-05-13
ACM Release Stream 5 | 2025-05-15: 2025-05-21; 2025-05-29: 2025-06-04 | Double check RH Recharge Day
MCE Release Stream 5 | 2025-05-15: 2025-05-21; 2025-05-29: 2025-06-03 | Double check RH Recharge Day
ACM Release Stream | 2025-05-15: 2025-05-21; 2025-06-05: 2025-06-11
MCE Release Stream | 2025-05-15: 2025-05-21; 2025-06-05: 2025-06-10
ACM Release Stream | 2025-06-12: 2025-06-18; 2025-06-26: 2025-07-02 | Update for US holiday
MCE Release Stream | 2025-06-12: 2025-06-18; 2025-06-26: 2025-07-01 | Update for US holiday
ACM Release Stream | 2025-06-12: 2025-06-18; 2025-07-03: 2025-07-09
MCE Release Stream | 2025-06-12: 2025-06-18; 2025-07-03: 2025-07-08
ACM Release Stream | 2025-07-10: 2025-07-16; 2025-07-24: 2025-07-30 | During OCP Y stream release window & subsequent ACM Y stream release target - there should only be one z-stream release planned
MCE Release Stream | 2025-07-10: 2025-07-16; 2025-07-24: 2025-07-29 | Highlight for ACM and MCE compatibility testing with OCP Y stream
[Note: Release Stream 1 Should Equal z-stream for OCP Y compatibility testing]
[Note: Release Stream 1 Should Equal z-stream for OCP Y compatibility testing]
| Train - 25 |  |  |  | Train - 26 |  |  |  | Train - 27 |  |  |  | Train - 28* |  |  |  | Train - 29 |  |  |  | Train - 30
ACM Operators
Train Start Dates | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07
Submariner | [24 empty] | Note: (Do not delete) - Submariner does not need to be included in ACM QE pipeline post ACM 2.11 release.
Global Hub
GateKeeper
VolSync
Milestones
BC: Bug Fix Cut Off
GA: General Availability
Phases
Development
Final Testing
ACM Z-Stream Release Schedule Reference - Historical